## Sheet1
Essential Skills Wales & Key Skills Levels 1-4 Action Plan
Task | Target Date | Responsibility | Completed | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-01 | 2013-10-01
Essential Skills Wales Electronic System
Review of System | on-going | MIS and Cross College Coordinator | 50%
11/12 Enrolments to be flooded into system | 2011-09-01 | MIS | 100%
Staff to check individual programme areas and session codes | 2011-10-15 | All staff, SLs | 100%
Staff to amend enrolments | 2011-11-01 | All staff, SLs | 100%
Staff to submit ESW and KS lists for completed portfolios Feb series | 2012-02-01 | All staff, SLs | 100%
Staff to submit ESW and KS lists for completed portfolios May series | 2012-05-01 | All staff, SLs | 100%
12/13 Enrolments to be flooded into system | 2012-09-01 | MIS | 100%
Staff to check individual programme areas and session codes | 2012-10-15 | All staff, SLs | 100%
Staff to amend enrolments | 2012-11-01 | All staff, SLs | 100%
Staff to submit ESW and KS lists for completed portfolios Feb series | 2013-01-10 | All staff, SLs | 0%
Staff to submit ESW and KS lists for completed portfolios May series | 2013-03-30 | All staff, SLs | 0%
Teaching and Learning
Essential Skills Wales to be identified on SoW | 2011-09-01 | All staff, SLs, Cross College Coordinator | 100%
WJEC documentation to implemented | on-going | All staff, SLs, Lead IVs, Cross College Coordinator | 100%
Training
Lead Internal Verifiers to carry out in house training to staff | on-going | ESW & KS Lead Ivs
Awarding body to carry out training on ICT | 2012-09-30 | WJEC | 100%
Awarding body to carry out training on AoN | 2012-01-30 | WJEC | 100%
Awarding Body to carry out training on Comm | 2012-02-28 | WJEC | 100%
Awarding Body to carry out training on Wider Skills | 2012-11-30 | WJEC | 100%
Cross-College Standarisation
Task | Target Date | Responsibility | Completed | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-01 | 2013-10-01
ESSLs meeting every fortnight | on-going | DHoS IES, ESSLs | 100%
ESW & KS Coordinator and Lead IVs meeting every month | on-going | ESW & KS Lead Ivs & Coordinator | 100%
Internal Verification (SSLs)
Complete WJEC audit sheets - deliverers and internal verifiers | yearly | Cross College Coordinator | 100%
Internal Verification carried out by SLs | 2012-02-28 | ESSLs Cross College Coordinator | 100%
Internal Verification of discussions, short talk, presentation | 2012-06-15 | ESSLs Cross College Coordinator | 100%
Internal Verification carried out by SLs | 2013-02-28 | ESSLs Cross College Coordinator | 0%
Quality Control (Lead Internal Verifiers)
ESW and KS Quality checks | 2012-03-01 | L IVs, Cross College Coordinator | 100%
ESW and KS Quality checks | 2012-07-01 | L IVs, Cross College Coordinator | 100%
ESW and KS Quality checks | 2013-03-01 | L IVs, Cross College Coordinator | 10%
External Verification (WJEC)
February Series | 2012-02-01 | WJEC | 100%
May Series | 2012-04-01 | WJEC | 100%
February Series | 2013-02-01 | WJEC | 0%
May Series | 2013-04-01 | WJEC | 0%
ESW & KS Submission
MIS to export submission data to Exams | 2012-07-15 | MIS, Cross College Coordinator | 100%
Task | Target Date | Responsibility | Completed | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-01 | 2013-10-01
Exams to submit lists to WJEC | 2012-07-15 | Exams, Cross College Coordinator | 100%
MIS to export submission data to Exams | 2013-07-14 | MIS, Cross College Coordinator | 0%
Exams to submit lists to WJEC | 2013-07-14 | Exams, Cross College Coordinator | 0%
ESW & KS Certification
Staff to check status of ESW and KS submission | 2012-07-15 | All staff, ESSLs, Cross College Coordinator | 100%
Staff to check status of ESW and KS submission
ESW & KS Data
Benchmarking data | 2012-09-30 | MIS, HoS, DHoS, ESSLs, Cross College Coordinator | 90%
NPTC Schools' Data | 2012-09-30 |  | 100%
Standards
Colegau Cymru Network meetings Termly | on-going | DHoS IES ESW & KS Cross College Coordinator | 100%
Cross college data | 2012-10-30 | MIS, HoS, DHoS, ESSLs, Cross College Coordinator | 1005%
Prior Achievements to be accredited | 2012-11-30 | All staff, ESSLs, Cross College Coordinator | 80%
Task | Target Date | Responsibility | Completed | 2011-09-01 | 2011-10-01 | 2011-11-01 | 2011-12-01 | 2012-01-01 | 2012-02-01 | 2012-03-01 | 2012-04-01 | 2012-05-01 | 2012-06-01 | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01 | 2013-06-01 | 2013-07-01 | 2013-08-01 | 2013-09-01 | 2013-10-01
Partnership
Feeder school data to be collated and flooed into QL | 2012-11-05 | MIS | 100%